Weekly Report

Andaman Aerodrome  ·  Silk Sky Air

From	Peter A. Moelgaard

To	Asaf Zmirly

Date	22 May 2026

Reporting period	Week 21  ·  16–22 May 2026

Next period	Week 22  ·  23–31 May 2026

Subject	Delivery review and forward plan

Three customer-visible deliverables shipped to production this week, supported by infrastructure improvements that reduce ongoing operational risk. Delivery is on plan. The forward week initiates three concurrent workstreams subject to access dependencies detailed in Section 3.

# 1  Results

Reporting period: 15–22 May 2026.

## Customer-facing deliverables

1. SkyStories editorial pipeline — production-ready. The Manager → Supabase → n8n → Strapi → public-site chain is fully operational across EN, TH, and RU locales. The editorial team can publish stories with linked keywords, tours, and media without engineering involvement. End-to-end test coverage is in place.

2. Customer payment confirmation email — live (SSA-621). Customers now receive a payment confirmation in their selected language the moment payment is registered. Resolves a recurring support thread.

3. Booking-note translations — complete (SSA-619). Thai and Russian labels added for customer-submitted note types. Closes a mixed-language inconsistency in non-English UIs.

## Infrastructure improvements

- Content-level audit added to n8n workflow deploys; identified three pre-existing production drifts this week.

- Retired sync_queue in favour of direct execution with fail-loud administrator alerts.

- Disabled Reporting Scheduler to free n8n plan quota for higher-priority workflows.

- Added three targeted indexes on the bookings read path; Manager response times improved.

- Established silkskyair-docs repository as the central location for cross-cutting planning and review documentation.

## Key metrics

| Metric | Value |
| --- | --- |
| Commits across all repositories | 65 |
| Active repositories touched | 11 |
| New shared repositories initialised | 4 |
| Production incidents | 0 |

# 2  Plan

Reporting period: 25–29 May 2026. Three concurrent workstreams, ranked by business priority.

## Initiative 1  ·  Partnership Portal — Round 3 review remediation

Objective: close the 22-item client review to clear the Partner Portal for launch.

| ID | Item | Status |
| --- | --- | --- |
| R1 | Back-office partner-create form clearing on save | Ready |
| R4 | Members → Clients terminology (Portal + Back Office) | Ready |
| R5 | Hide Commission Rate + Performance Overview cards | Ready |
| R7 | + Invite Member → + Invite Team | Ready |
| R8–R11 | i18n keys, stepper labels, Submit Booking CTA | Ready |
| R12 | Passenger nationality / weight save (FK violation) | Ready |
| R13–R16 | Direct → Full / Indirect → Net + commission math | Ready |
| R19 | TOTAL AMOUNT parity on indirect payment dialog | Ready |
| R22 | Archive-clients feature | Ready |
| R20a | Back-office notification bell on cancellation | Ready |

Target: 15 of 22 items shipped to staging by Friday. Remaining items are access-blocked (see Section 3).

## Initiative 2  ·  Member Portal — 1st Review remediation, Phase 1

Objective: begin the 33-item Member Portal review (MP1, 19 May 2026). Phase 1 is a low-risk trim; Phase 2 (amendment-payment lifecycle) follows in subsequent weeks.

| Workstream | Scope |
| --- | --- |
| MP1-W01 | Disable check-in flow (commented, not deleted); deferred to Phase 2 per client direction |
| MP1-W02 | Magic-link-only authentication on the Member Portal |
| MP1-W03 | Replace bucketed passenger-weight dropdown with numeric kg input |
| MP1-W11 | Author Booking Status reference document |

Target: Phase 1 workstreams complete; Phase 2 (MP1-W06 state machine) initiated.

## Initiative 3  ·  Meta CAPI / Pixel Purchase integration

Objective: restore conversion signal to Meta. Dual-track (browser Pixel + server-side CAPI, shared event_id) is required because Thai customers commonly initiate on desktop and complete payment via PromptPay on mobile, losing the Pixel signal.

| # | Task | Notes |
| --- | --- | --- |
| 1 | Capture fbclid / _fbp / _fbc on WWW landing | Consent-gated |
| 2 | Install Meta Pixel; fire Purchase on confirmation | Consent-gated |
| 13 | Extend api.bookings view with new fields | DB migration |
| 14 | Add analytics.events_sent table | Idempotency + observability |
| 6 | Revise meta-capi-purchase.json n8n workflow | Per revised design |

Target: frontend capture and Pixel live; DB foundations landed; workflow revised pending credential. End-to-end verification expected the following week.

# 3  Required actions

The following items require external action and currently block specific deliverables.

| Action | Owner | Initiative | Unblocks |
| --- | --- | --- | --- |
| Grant read access to silkskyair-account repository | Asaf | Partner Portal | R3 |
| Grant access to n8n workflows repository / cloud workspace | Asaf | Partner Portal + Meta CAPI | R2, R20-email, Meta deploy |
| Provision Omise keys in Partner Portal Vercel project | Asaf | Partner Portal | R17, R18 |
| Provide specification for Available Tours widget | Product | Partner Portal | R6 |
| Provide Meta access token for CAPI credential | Marketing | Meta CAPI | Workflow activation |
| Confirm BookingPaidInFull target status | Asaf | Member Portal | MP1-W06 |

# 4  Status and risk

## Confidence by initiative

| Initiative | Confidence | Caveat |
| --- | --- | --- |
| Partnership Portal (unblocked subset) | High | Blocked items contingent on Section 3 |
| Member Portal Phase 1 | High | Low-risk, well-scoped |
| Meta CAPI | Medium | Dependent on Meta credential provisioning |

## Risks under observation

- Member Portal Phase 2 (amendment-payment lifecycle) is the largest unknown of the coming two to three weeks. It touches the booking state machine, payment flow, Manager UI, and customer email templates. A 30-minute walkthrough with operations is recommended once Phase 1 lands.

- Meta CAPI verification depends on staging traffic. A quiet period may extend end-to-end confirmation in Meta Events Manager by approximately one day.

# A  Appendix A  ·  Notion task register

For traceability, the planned forward-week work decomposes into the following Notion tasks. Identifiers map to the source planning documents in silkskyair-docs/plans/.

## A.1  Partnership Portal — Round 3 review

Source: partnership-portal-client-review.md. Atomic tasks selected for landing in Week 22.

| Task ID | Title | Repository |
| --- | --- | --- |
| R1-T1 | Persist partner data after save on Back-Office create form | silkskyair-manager |
| R3-T1 | Consolidate role-label rendering via shared formatRoleLabel helper | silkskyair-partner |
| R4-T1 | Rename Members → Clients in Partner sidebar navigation | silkskyair-partner |
| R4-T2 | Update Clients page heading and subtitle | silkskyair-partner |
| R4-T3 | Rename Add Member button to Add Client | silkskyair-partner |
| R4-T4 | Update i18n entries for Members → Clients | silkskyair-api |
| R4-T6 | Update Members → Clients in Back-Office sidebar and pages | silkskyair-manager |
| R5-T1 | Hide Commission Rate + Performance Overview cards on dashboard | silkskyair-partner |
| R7-T1 | Rename Team invite button to + Invite Team | silkskyair-partner |
| R8-T1 | Add translation for team.status.archived | silkskyair-api |
| R8-T3 | Remove unused create.finalPriceNote reference | silkskyair-partner |
| R9-T1 | Fix stepper step 4 label to Shared/Private Flight | silkskyair-partner |
| R10-T1 | Rename final-step CTA to Submit Booking | silkskyair-partner |
| R12-T1 | Add countries endpoint for nationality dropdown | silkskyair-partner |
| R12-T2 | Replace nationality free-text input with ISO country select | silkskyair-partner |
| R13-T1 | Rename Direct Payment → Full Payment label | silkskyair-api |
| R14-T1 | Rename Indirect Payment → Net Payment label | silkskyair-api |
| R15-T1 | Hide Withholding Tax row in indirect payment breakdown | silkskyair-partner |
| R16-T1 | Correct Net to Partner calculation for indirect payment | silkskyair-partner |
| R16-T2 | Mirror commission math fix in settlement INSERT route | silkskyair-partner |
| R19-T1 | Render TOTAL AMOUNT card on indirect payment dialog | silkskyair-partner |
| R20-T1 | Insert notification on BookingCancellationRequested trigger | silkskyair-api |
| R20-T2 | Mount notification bell + API in Back-Office header | silkskyair-manager |
| R22-T1 | Add archived_at column + archive_member RPC | silkskyair-api |
| R22-T2 | Add Archive action and Show-archived toggle to Clients list | silkskyair-partner |

## A.2  Member Portal — 1st Review, Phase 1

Source: member-portal-1st-review-2026-05-19.md. Workstreams selected for Week 22.

| Task ID | Title | Repository |
| --- | --- | --- |
| MP1-W01-T1 | Comment out check-in route, page, and step components | silkskyair-member |
| MP1-W01-T2 | Disable booking_checkin_state queries and middleware bypasses | silkskyair-member |
| MP1-W01-T3 | Remove Check-In CTAs and banners from booking detail | silkskyair-member |
| MP1-W02-T1 | Add magic-link-only context detection helper | silkskyair-member |
| MP1-W02-T2 | Gate sign-in form password section behind magicLinkOnly prop | silkskyair-member |
| MP1-W03-T1 | Replace WeightRangeSelector with positive-numeric kg input | silkskyair-member |
| MP1-W03-T2 | Update passenger weight validation to positive numeric | silkskyair-member |
| MP1-W11-T1 | Author Booking Status reference document | silkskyair-docs |
| MP1-W11-T2 | Capture Advance Aviation weight rationale in docs | silkskyair-docs |

## A.3  Meta CAPI / Pixel — Purchase integration

Source: meta-capi-purchase-integration.md. Tasks selected for Week 22.

| Task ID | Title | Repository |
| --- | --- | --- |
| CAPI-1 | Capture fbclid / _fbp / _fbc on landing (consent-gated) | silkskyair-www |
| CAPI-2 | Install Meta Pixel; fire Purchase on confirmation page | silkskyair-www |
| CAPI-3 | Extend BookingStore and SubmitBookingPayload types | silkskyair-www |
| CAPI-4 | Thread fbclid/_fbp/_fbc/landing_url into client_interactions | silkskyair-www |
| CAPI-6 | Revise meta-capi-purchase.json workflow per new design | silkskyair-workflows |
| CAPI-13 | Extend api.bookings view to surface Meta fields | silkskyair-api |
| CAPI-14 | Add analytics.events_sent table for idempotency | silkskyair-api |
| CAPI-15 | Document Meta token rotation procedure | silkskyair-workflows |

Tasks 5, 7–12 (n8n credential creation, registration, verification, deploy) are sequenced after credential provisioning and unblock automatically once the Meta access token is available.